## Sheet1
Change Request id | Change Request id | Submitted by | Description | Reason/Justification | Impact Analysis | Priority | Approval Status | Approved by & date
1 | 2026-06-12 | Exam Controller | online exam registeration module for students | reduce paperwork,redue queues,donot visit university as a inperson or registeration | Core Module,need database,login/signup form UI,Exam registeration form UI | High | Approved | Project Manager 13 June-2026
2 | 2026-06-11 | Project Manager | Need Admin Dashborad,generate report for student grade,download/export excel format | Admin/exam controller need report without IT help. | Admin dashborad,export business logic | Medium | Approved | Project Manager 13 June-2026
3 | 2026-06-10 | Student affairs | Auto generate and email roll no slip as PDF |  | PDF library needed Email server config requred | Medium | Approved | Project Manager 13 June-2026
4 | 2026-06-09 | Finance Dept | Add penalty fee auto-calculation for late registration | Manual penalty calculation causes errors and disputes | small logic change in payment module | Low | Approved | Under Review